## Sheet
Project Name: | Agile Manifesto
Stakeholders/Users: | Students, Instructor, Software Engineering Team
Created By: | Product Owner (Instructor)
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria | Story Points | Sprint | Sub Tasks
Create a web-based Agile Manifesto platform | US001 | Homepage for Agile Manifesto | As a user, I want to see a visually appealing homepage with navigation, so that I can explore the Agile Manifesto. | New | The homepage is visually designed, includes an introduction to Agile and its history, and provides navigation to other sections. | 5 | 1 | Subtask 1.1.1: Create wireframes for the homepage. Subtask 1.1.2: Develop the homepage layout using HTML and CSS. Subtask 1.1.3: Add an introduction to Agile and its history. Subtask 1.1.4: Implement navigation links to other sections. Subtask 1.1.5: Conduct user testing and gather feedback.
Create a web-based Agile Manifesto platform | US002 | Agile Values and Principles | As a user, I want an interactive page explaining Agile values and principles, so that I can understand Agile. | New | The page displays the four core Agile values, explains 12 principles interactively, and provides examples for each value and principle. | 8 | 2 | Subtask 2.1.1: Create a page layout for the four Agile values. Subtask 2.1.2: Develop interactive elements to explain the 12 principles. Subtask 2.1.3: Add examples to illustrate each Agile value and principle. Subtask 2.1.4: Review the content with the instructor for feedback. Subtask 2.1.5: Test the interactivity and responsiveness of the page.
Create a web-based Agile Manifesto platform | US003 | Resource Library | As a user, I want a library of Agile practices, so that I can access resources like Scrum, Kanban, etc. | New | The library is designed to display Agile practices, includes downloadable resources, and provides search and filter functionalities. | 8 | 3 | Subtask 3.1.1: Design the library page layout. Subtask 3.1.2: Populate the library with resources (Scrum, Kanban, templates, guides). Subtask 3.1.3: Develop search functionality for the library. Subtask 3.1.4: Implement filters for sorting resources by category. Subtask 3.1.5: Test the search and filter functionalities.
Create a web-based Agile Manifesto platform | US004 | Collaboration Features | As a user, I want to discuss and comment on Agile principles, so that I can collaborate and share ideas. | New | Users can post in a discussion forum, comment on principles and resources, and collaborate after user authentication. | 13 | 4 | Subtask 4.1.1: Design a user-friendly discussion forum layout. Subtask 4.1.2: Develop backend APIs for forum posts and comments. Subtask 4.1.3: Implement user authentication for posting and commenting. Subtask 4.1.4: Integrate the frontend with backend APIs. Subtask 4.1.5: Test the collaboration features (posting, commenting, authentication).
|  |  |  | JIRA URL | https://sirisharamya.atlassian.net/jira/software/projects/AM/boards/5/timeline