## Sheet1
Task Name | Epic | Story/Feature | Subtask | Story Points | Sprint | Assignee | Status | Due Date
Create Agile Manifesto Platform | Epic | Homepage for Agile Manifesto | Create wireframes | 3 | Sprint 1 | Developer 1 | In Progress | 2025-01-10
|  |  | Develop HTML and CSS | 3 | Sprint 1 | Developer 2 | To Do | 2025-01-12
|  | Agile Values and Principles | Implement interactive principles | 5 | Sprint 2 | Developer 3 | Not Started | 2025-01-24
Design Resource Library | Epic | Resource Library | Design library interface | 8 | Sprint 3 | Developer 1 | Not Started | 2025-02-04
Develop Discussion Forum | Epic | Collaboration Features | Develop discussion forum | 13 | Sprint 4 | Developer 2 | Not Started | 2025-02-15